## Action tracker
COMMUNITY FEEDBACK ACTION TRACKER |  |  |  | PLEASE NOTE: In case there are broader action plans for the project or operation, make sure to include the recommendations and actions into these broader plans to avoid feedback to be treated in a silo.
This table keeps track of the recommended actions to address community feedback received by the [name of the organisation/coordination group] in [country or region]. It is managed and updated by [name] ([email])
DATE Date when the action was agreed upon | LINK Link to report if available | TOPIC Topic the action relates to | ISSUE Short description of the issue which is to be addressed | RECOMMENDATION Short description of the suggested action to be taken | SECTOR/ DEPARTMENT Sector or department responsible for taking action | FOCAL POINT Name of the person responsible for action and/or follow-up | ACTION TAKEN Short description of the action taken to address the issue | STATUS Dropdown menu | LINK TO OUTPUT Any links to outputs if available | CLOSING THE LOOP Who will inform the individual/ community of the decision/ action? | CLOSING THE LOOP How will the loop be closed? | CLOSING THE LOOP When was the loop closed with individual/community?
2022-01-31 | [link to report if available online] | Questions about COVID booster shots | Lots of rumours and unclarity about the necessity of booster shots | Organise an inter-active radio session on the topic, inviting a medical doctor to answer questions | RCCE | [name] | Inter-active radio session took place on 9 February | Done | [link to the recording of the session] | CEA Team | Through the radio program | Closed on 9 Feb
2022-01-31 | [link to report if available online] | Questions about COVID booster shots | Lots of rumours and unclarity about the necessity of booster shots | Update the FAQ for volunteers conducting RCCE activities to ensure sufficient information on booster shots is included | Health | [name] | Drafted new content is waiting to be cleared by the technical lead | Ongoing |  | Volunteers | Through normal community activities once FAQ is updated | Not yet closed
2022-02-01 | [link to report if available online] | Dissatisfaction with the amount of cash transfers | Recipients of cash transfers have been requesting an increase of the amount provided | Gather more information to understand which groups are facing the biggest issues | Cash | [name] | Deep analysis of the feedback data has been conducted which showed that this feedback has been mainly shared by community members in the East of the district. Focus group discussions are planned to better understand the concerns. | Ongoing |  | Cash technical leads | Through community meetings | Updated community leaders of need for FGDs on Feb 13.

## Sheet2
Status options:
not started
ongoing
done